## ACTION register
1 Page Project™ is provided by UNIK Partner Sweden AB. Revision: 1.0. See www.unikpartner.com for updates and more templates.
|  |  |  | Current date: | 2019-11-15
|  | ACTION register | 1 Page Project™
Id | Date decided | Action Agreed to be performed | Responsible | Deadline Agreed to be completed by | Closed Actual completed date | Status/Comment
1 | 2018-03-25 | Inform about suggested change request | John Smith | 2019-12-27 | 2019-12-28
2 | 2018-03-27 | Execute change request | John Smith | 2018-09-25 |  | 2018-03-27 Working on this right now/JS
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## RISK register
1 Page Project™ is provided by UNIK Partner Sweden AB. Revision: 1.0. See www.unikpartner.com for updates and more templates.
[9 empty] | Current date: | 2019-11-15
|  | RISK register |  | 1 Page Project™
[5 empty] | (1-5; 5 high) | (1-5; 5 high) | (1-25; 25 high)
Id | Date discovered | Discovered by | Risk description | Impact of Risk | Probability | Impact | Risk Value | Respone to the Risk or Issue | Responsible | Status | Comment
1 | 2019-05-20 | John Smith | The components will not arrive in time | Delay - sub project can't deliver in time | 3 | 4 | 12 | Avoid - talk to the supplier | Carl Adams | Avoided | 2019-05-28 supplier confirmed delivery date
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0

## ISSUE register
1 Page Project™ is provided by UNIK Partner Sweden AB. Revision: 1.0. See www.unikpartner.com for updates and more templates.
[6 empty] | Current date: | 2019-11-15
|  | ISSUE register |  | 1 Page Project™
Id | Date discovered | Discovered by | Issue description | Impact of Risk or Issue | Respone to the Risk or Issue | Responsible | Status | Comment
1 | 2018-04-27 | Dan John | Strike at airport | Delay - delivery of components | Inform production manager and report consequence to project manager | Sam Lee | Ongoing | 2018-05-26 production manager on vacation; e-mail sent to CMO
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## DECISION register
1 Page Project™ is provided by UNIK Partner Sweden AB. Revision: 1.0. See www.unikpartner.com for updates and more templates.
|  |  | Current date: | 2019-11-15
|  | DECISION register | 1 Page Project™
Id | Date decided | Decision | Decision impact | Decided by
1 | 2018-03-27 | Project change request approved | Marketing communcation affected - All persons producing marcom material needs to be informed. | Martin Tilly
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Risk assessment guide
Value | (Probability X Impact)
<10 | Marked green
19 to 20 | Marked yellow
>=20 | Marked red
Probability |  | Impact | choose highest value of the below if multiple risk categories (time, cost and quality)
Value | Description | Value | Description if time risk | Description if cost risk | Description if quality risk
1 | < 25% probability that it will happen | 1 | < 10 days | < 10 kSEK | Minor reduced quality on apperence but overall benefits will be met
2 | 25-49% probability that it will happen | 2 | 10-19 days | 10-19 kSEK | Minor reduced functionallity but overall benefits will be met
3 | 50-74% probability that it will happen | 3 | 20-29 days | 20-29 kSEK | Major reduced functionallity but overall benefits will be met
4 | 75-89% probability that it will happen | 4 | 30-39 days | 30-39 kSEK | Minor overall project benefits will not be met
5 | > 90 % probability that it will happen | 5 | >=40 days | >=40 kSEK | Major overall project benefits will not be met