## Lesson Log
1 Page Project™ is provided by UNIK Partner Sweden AB. Revision: 1.0. See www.unikpartner.com for updates and more templates.
|  | Lesson Log | 1 Page Project™
Id | Date identified | Identified by | Category | Lesson detail | Priority
1 | 2018-09-07 | John Smith | Supplers | Faulty products in the first batch delivered from Suppler Z, needs to be sent back immediately for rework otherwise the supplier will continue to deliver faulty products for the upcoming 3 batches. | High
2 | 2018-09-09 | John Smith | Financial | Dollar exchange rate have high impact on the standard production cost of product X. | High
3 | 2018-09-09 | Carl Adams | Project Management | When the projects client was on vacation (and no delegation of decision was formalized) the project halted. | High
4 | 2018-09-11 | Anna Andersson | Supplers | When Supplier Y forecast that they might not meet deadline, it's very likley that they will exceed it. | Medium
5 | 2018-09-12 | Robert Johansson | Supplers | Continue to use Martin from Supplier X as a team leader, he have always delivered in time. | Low
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20