## Slide 1: Project Management Report
Project Name: Project X
Date of this report: 2019-06-17
Project objectives:
Develop a new … and transfer data from...
UNIK Template: Project Management Report UPABT001719 Rev 1 2019-06-17
Key performance indicators
MS 1
MS 2
MS 3
MS 4
MS 5
Date | Summary of changes
2019-04-28 | Mile stone 4 date update; originally 2019-09-14
2019-05-18 | Scope reduced; deliverable X removed
Indicator | Status | Comments
Time |  | N/A
Cost |  | N/A
Quality |  | A faulty unit was found during a randomized inspection. All units to be inspected now.
Scope |  | The sr. user of the project wants to add new items into mile stone 3. Await decision from board.
Benefits |  | N/A
Risk |  | N/A
History of major project changes:
Other performance indicators
Indicator | Status | Comments
Resources |  | R&D resources needed in July are not locked. R&D Manager is looking for new consultants.
Project Manager’s impression |  | Project team motivation is low due to poor test results. Team building day is booked.
Overall project performance | Comments
 | The project is currently having issues with R&D resources in July. A potential scope creep could affect the plan. Quality of delivered units could be an issue. Project team motivation is currently low.
Financial summary